## Test Plan
Section | Details
Project Name | Employee Attendance & Authentication System
Prepared By | Ashish Gaikwad
Testing Type | Manual Testing
Scope | Sign Up, Login, Forgot Password, OTP Login
Out Of Scope | Backend APIs, Performance Testing, Load Testing
Test Approach | Scenario creation → Test case design → Execution → Defect logging
Entry Criteria | Application URL active, test data prepared
Exit Criteria | All critical test cases executed and defects addressed
Risks | OTP delay, incorrect validation messages
Mitigation | Retesting, coordination with developers
Deliverables | Test Plan, Test Cases, Test Scenario, Execution Report, Defect Log